## Slide 1
Monthly project health synthesis
Both sample implementations need intervention before more near-term dates turn late.
2
projects assessed
2/2
rated Red
66
active overdue tasks
120
active tasks due in 14 days
Assessment date: 2026-07-09. Inputs: two Excel project plans and comment sheets.
01

## Slide 2
PROJECT HEALTH REPORTING AGENT
The portfolio risk pattern is schedule-led, not isolated to one project
Across both plans, the strongest signal is schedule pressure: active overdue work, active Red tasks, and a large amount of work due within the next two weeks.
Budget burn cannot be evaluated from the supplied files, so the agent discloses it as missing rather than inventing a score.
Chart: Near-term schedule load
| Titan S2P | UniSan S2P
Overdue active | 22 | 44
Due in 14 days | 50 | 70
02

## Slide 3
PROJECT HEALTH REPORTING AGENT
Titan needs dependency closure; UniSan needs schedule recovery
Titan S2P
22 overdue
Progress is ahead of elapsed time, but on-hold D&B work, JDE mapping, and workshop impacts keep the project Red.
UniSan S2P
44 overdue
The project is 17.7 percentage points behind elapsed time and has heavier Red schedule concentration.
Common issue
120 due soon
A large two-week task load means the portfolio can create more misses unless closure cadence tightens now.
03

## Slide 4
PROJECT HEALTH REPORTING AGENT
The biggest risks are operational, not measurement artifacts
Trend
Evidence
Executive implication
Schedule pressure
66 active overdue tasks and 67 active Red tasks
Recovery needs active owner-level management, not passive reporting.
Near-term load
120 active tasks due by 2026-07-23
More slippage is likely without a two-week closure plan.
Dependency blockers
Titan comments cite impacted workshops, JDE mapping, meetings, and PH cleanup
Client and internal dependencies need steering-level escalation.
Data gap
No budget fields in either workbook
Leadership cannot yet connect delivery health to margin impact.
04

## Slide 5
PROJECT HEALTH REPORTING AGENT
Recommended action is a two-week control cycle
1
Recover
Create a daily closure list for overdue Red tasks and overdue active milestones.
2
Escalate
Move client dependencies and on-hold items into the weekly steering forum with named decision owners.
3
Prevent
Pre-review all tasks due in the next 14 days before they become overdue.
4
Instrument
Add budget planned, actual, forecast, and sentiment fields to strengthen future health scoring.
05

## Slide 6
PROJECT HEALTH REPORTING AGENT
The agent should become the weekly health operating rhythm
Monday
Read latest project plans and comments.
Tuesday
Publish Red/Amber deltas and overdue owner list.
Wednesday
Use steering forum for dependency decisions.
Friday
Update client-ready summary and refresh monthly trend deck.
Decision needed: confirm a two-week recovery owner for each Red project and add budget data to the standard plan export.
06